## QM_Report
BOSCH |  | NOC Quality Finding Track | [6 empty] | Resp. CI/OSR-CN QMM-AB
| Finding Source |  |  | Finding Level | Finding Resp. | Repeat Fault |  | Acknowledge Status |  | Finding Status
| NOC Daily QC |  |  | Critical | Cheng Vicky | Yes |  | Fully accept |  | Open
| User Feedback |  |  | Major | Fan Yixiang | No |  | Partial accpet |  | Resolved
| WAN PMA report |  |  | Minor | Francesco Abrahao |  |  | Not accept |  | Cancelled
| CI/OSN |  |  |  | Figueira Jose
| CI/OSN2 |  |  |  | Gao Allen
| CI/OSN3 |  |  |  | Liu Jing
| CI/OSN 6/7/8 |  |  |  | Liu Athena
| CI/OSR5-SG |  |  |  | Liu Roy
| CI/OSR1-AM |  |  |  | Shi Leo
| NOC QM |  |  |  | Shou Cabby
| Dept. QM |  |  |  | Wang Eden
Wang Mingxing
Xia Elaine
Xie David
Yan Jun
Farinelli Alexandre
Zhu Frank
Zhu Lin
XU Gary
All
Zhang Yupeng
Lu Yuan
Report Date | Finding Source | Ticket No. | Finding Description | Finding Level | Finding Resp. | Repeating Fault | Quality Measures Track | Acknowledge Status | If not fully accept, put reason here | Finding Status
2018-01-02 | NOC Daily QC | INC000013052055 | Resolution and resolution categorization do not fit | Major | Zhang Yupeng | No | 1/2/2108 Zhu Lin informed Yupeng to check and correct | Fully accept |  | Resolved
2018-01-02 | NOC Daily QC | INC000013051783 | CI-Unavailability was not related for Gold site complete outage | Major | Farinelli Alexandre | Yes | 1/2/2018 Zhu Lin highlighted to Alexandre to related ci-unavailability for gold site complete outage | Fully accept |  | Resolved
2018-01-03 | NOC Daily QC | INC000013058233 | Owner group wrong, connection ID 1200, owner group should be Network WAN EMEA | Major | Farinelli Alexandre | Yes | 1/3/2018 Zhu Lin highlighted to Alexandre to choose owner group according to connection ID | Fully accept |  | Resolved
2018-01-03 | WAN PMA report | INC000013051783 | CI-unavailability was not related | Major | Farinelli Alexandre | Yes | 1/8/2018 Zhu Lin highlighted to colleague to do not forget to relate CI-Unavailability and informed all via email | Fully accept |  | Resolved
2018-01-03 | WAN PMA report | INC000013027286 | WAN ticket format was not used | Major | Farinelli Alexandre | Yes | 1/8/2018 Zhu Lin reminded the colleague to update the ticket format for coming tickets | Fully accept |  | Resolved
2018-01-03 | WAN PMA report | INC000013023607 | SLA violated 2h35mins, but not recoreded in resolution | Major | Zhang Yupeng | No | 1/8/2018 Zhu Lin asked all colleague to do not forget SLA when updating rfo | Not accept | the resolution was changed to update rfo, sla violation was missed | Cancelled
2018-01-03 | WAN PMA report | INC000013008046 | maintenance, didn't treat the ticket as maintenance ticket but as false alarm | Major | Francesco Abrahao | No | 1/8/2018 reminded colleagues to follow the correct working procedure | Fully accept |  | Resolved
2018-01-08 | NOC Daily QC | INC000013076539 | Short time outage on which line? In resolution,it's short outage on primary line, then, incident type should be User Service Request, not User service restoration | Major | Figueira Jose | No | 1/8/2018 Zhu Lin reminded Jose to check and update the ticket to make the ticket right | Fully accept |  | Resolved
2018-01-10 | NOC Daily QC | INC000013080084 INC000013097582 | Impact for gold site partial outage wrong | Major | Francesco Abrahao | No | 1/10/2018 Zhu Lin informed Franceco to follow the WAN ticket priority matrix | Fully accept |  | Resolved
2018-01-15 | NOC Daily QC | INC000013120311 | Summary format wai not used. Incident type is not correct | Major | Francesco Abrahao | Yes | 1/15/2018 Zhu Lin informed Franceso to have a check and take care in future | Fully accept |  | Resolved
2018-01-19 | NOC Daily QC | INC000013138766 | Owner group not correct for 1279 | Major | Zhang Yupeng | Yes | 1/19/2018 Zhu Lin reminded Yu peng not to forget to change owner group for coming ticktes | Fully accept |  | Resolved
2018-01-24 | NOC Daily QC | 5560037 | Customer want to add four entries below, two entries source IP address mask is /24. Others mask is /23. I wrote all of them to /24. | Major | Zhang Yupeng | No | 1/24/2018 Zhu Lin asked Yupeng to correct and be careful about the mask | Fully accept |  | Resolved
2018-02-01 | NOC Daily QC | INC000013220775 | CI-Unavailabity was 03:40, the sla is violated, not no sla violation | Major | Figueira Jose | No | 2/1/2018 Zhu Lin informed Jose to have a check and calculate the sla violation time correctly. | Fully accept |  | Resolved
2018-02-06 | WAN PMA report | INC000013059164 | Owner group wrong | Major | XU Gary | Yes | 2/7/2018 Zhu Lin Highlighted to colleagues not forget to update owner group refer to the connection ID | Fully accept |  | Resolved
2018-02-06 | WAN PMA report | INC000013097582 | Owner group wrong | Major | Francesco Abrahao | No | 2/7/2018 Zhu LinHighlighted to colleagues not forget to update owner group refer to the connection ID | Fully accept |  | Resolved
2018-02-06 | WAN PMA report | INC000013096033 | incident type wrong,partial outage, the incident type should be User Service Request | Major | Farinelli Alexandre | Yes | 2/7/2018 Zhu Lin Highlighted to colleagues to select right incident type for partial outage or complete outage | Fully accept |  | Resolved
2018-02-06 | CI/OSN 6/7/8 | INC000013194874 | did not log on switch to check interface status | Major | Liu Roy | No | 2/6/2018 Liu Roy For this case, NOC agnet did not strictly follow up the LAN process, Highlighted this point to them again : Make call is the first choice, if local contact is not in office time but site is 7*24, call to LAN redline should be made. | Fully accept |  | Resolved
2018-02-06 | CI/OSN 6/7/9 | INC000013236856 | sent mail to inform LAN person in Mid-night, did not make call | Major | Figueira Jose | Yes | 2/6/2018 Liu Roy 'Highlight to all NOC shift to do sh test for interface down alarm on switch, And for ticket track , also highlight to team members to follow up ticket every day, to avoid cases that no one follow up in a long time. | Fully accept |  | Resolved
2018-02-09 | NOC Daily QC | INC000013244412 | Summary format wai not used. Incident type is not correct | Major | Farinelli Alexandre | Yes | 2/9/2018 Zhu Lin infomed Alex to correct and take care in future | Fully accept |  | Resolved
2018-02-22 | NOC Daily QC | INC000013290182 | owner group wrong | Major | Zhang Yupeng | No | 2/22/2018 Zhu Lin informed Yupeng to correct and take care in future. | Fully accept |  | Resolved
2018-02-22 | NOC Daily QC | INC000013317638 | maintenance in local provider side,resolution categorization tier 2 should be network outage | Major | Gao Allen | No | 2/26/2018 Zhu Lin informed Allen to correct and take care in future. | Fully accept |  | Resolved
2018-02-22 | NOC Daily QC | INC000013288963 | SLA violation time missed | Major | Zhang Yupeng | No | 2/22/2018 Zhu Lin informed Yupeng to correct and take care in future. | Fully accept |  | Resolved
2018-02-26 | NOC Daily QC | INC000013344731 | Summary format wai not used | Major | Farinelli Alexandre | Yes | 2/26/2018 Zhu Lin informed Alex to correct and take care in future. | Fully accept |  | Resolved
2018-02-26 | NOC Daily QC | INC000013341467 | Owner group not correct for 1279 | Major | Gao Allen | No | 2/22/2018 Zhu Lin informed Allen to correct and take care in future. | Fully accept |  | Resolved
2018-02-27 | NOC QM | n.a | Miss checking escalation email | Critical | Cheng Vicky | No | 2/27/2018 David reminded and highlighted to colleagues to check escalation email in time | Fully accept |  | Resolved
2018-02-27 | NOC QM | n.a | Miss checking escalation email | Critical | XU Gary | No | 2/27/2018 David reminded and highlighted to colleagues to check escalation email in time | Fully accept |  | Resolved
2018-02-27 | NOC QM | n.a | Miss checking escalation email | Critical | Zhu Frank | No | 2/27/2018 David reminded and highlighted to colleagues to check escalation email in time | Fully accept |  | Resolved
2018-02-27 | NOC QM | n.a | Miss checking escalation email | Critical | Figueira Jose | No | 2/27/2018 David reminded and highlighted to colleagues to check escalation email in time | Fully accept |  | Resolved
2018-02-27 | NOC QM | n.a | Miss checking escalation email | Critical | Francesco Abrahao | No | 2/27/2018 David reminded and highlighted to colleagues to check escalation email in time | Fully accept |  | Resolved
2018-02-28 | NOC Daily QC | INC000013347719 | incident type , operational categorization tier 1 not correct for no connection? | Major | XU Gary | No | 2/28/2018 Zhu Lin asked Gary to correct and take care in future | Fully accept |  | Resolved
2018-03-05 | WAN PMA report | INC000013343199 | Owner group should be Network WAN AP for connection ID 3830 | Major | XU Gary | Yes | 3/5/2018 Zhu Lin highloghted to Gary and all NOC shift colleague s to select right owner group according to connection ID | Fully accept |  | Resolved
2018-03-05 | WAN PMA report | INC000013341337 | No connection, incident type should be Infrastructure Restoration | Major | Fan Yixiang | No | 3/5/2018 Zhu Lin Highlighted NOC colleagues to choose right Incident type and Operational Categorization Tier 1 | Fully accept |  | Resolved
2018-03-05 | WAN PMA report | INC000013336468 | SLA Viiolated how long was not recorded | Major | Francesco Abrahao | No | 3/5/2018 Zhu Lin 'Highlighted NOC incident handling colleagues to record the SLA violated time according to the requirement. | Fully accept |  | Resolved
2018-03-05 | WAN PMA report | INC000013327487 | Power supply issue, not clear about power issue on which side | Major | Zhu Frank | No | 3/5/2018 Zhu Lin 'Highlighted NOC incident handling colleagues to record clearly in resolution what caused the failure | Fully accept |  | Resolved
2018-03-06 | NOC Daily QC | INC000013231413/INC000013352899 | Service + Chosed wrong for WAN tickets | Major | Zhang Yupeng | No | 3/6/2018 Zhu Lin informed Yupeng to be careful to choose service+ in future | Fully accept |  | Resolved
2018-03-08 | NOC Daily QC | INC000013421575 | Resolution categorization tier 2 is not correct for power issue at customer side | Major | Francesco Abrahao | Yes | 3/8/2018 Zhu Lin informed Francesco to correct and take care in future | Fully accept |  | Resolved
2018-03-08 | NOC Daily QC | INC000013379089 | Incident type not correct for no connection | Major | Yan Jun | No | 3/8/2018 Zhu Lin informed Yan Jun to correct and take care in future | Fully accept |  | Resolved
2018-03-07 | CI/OSN3 | INC000013428064 | Owner group is wrong for Connection ID 1200 | Major | Figueira Jose | Yes | 3/7/2018 Armin required Jose to correct | Fully accept |  | Resolved
2018-03-13 | NOC Daily QC | INC000013451636 | No planned maintennace at provider site, the resolution categorization tier2 should not be power, should be network outage | Major | Figueira Jose | Yes | 3/13/2018 Zhu Lin informed Jose to check and correct | Fully accept |  | Resolved
2018-03-13 | NOC Daily QC | INC000013448083 | Power outage at customer site, the resolution categorization tier2 should be power | Major | Lu Yuan | No | 3/13/2018 Zhu Lin informed Eric to check and correct | Fully accept |  | Resolved
2018-03-15 | NOC Daily QC | INC000013463559 | Owner group not correct | Major | Lu Yuan | No | 3/192018 Zhu Lin informed Eric to check and correct | Fully accept |  | Resolved
2018-03-20 | NOC Daily QC | INC000013421575 | Power outage at customer site, the resolution categorization tier2 should be power | Major | Francesco Abrahao | Yes | 3/20/2018 Zhu Lin informed Francesco to correct and take care in future | Fully accept |  | Resolved
2018-03-22 | NOC Daily QC | INC000013498652 | Incident type was not updtaed | Major | Lu Yuan | No | 3/22/2018 Zhu Lin informed Eric to check and correct | Fully accept |  | Resolved
2018-03-22 | NOC Daily QC | INC000013502114 | Summary not good | Major | Lu Yuan | No | 3/22/2018 Zhu Lin informed Eric to check and correct | Fully accept |  | Resolved
2018-04-04 | WAN PMA report | INC000013532025 | Power issue at customer side, the resolution categorization tier 2 should be Power | Major | XU Gary | Yes | 4/4/2018 Zhu Lin highlighted in PMA found issue | Fully accept |  | Resolved
2018-04-04 | WAN PMA report | INC000013528668 | SLA violated time was not recorded | Major | Lu Yuan | No | 4/4/2018 Zhu Lin talked to Lu Yuan f2f and reminded him to take care in future | Fully accept |  | Resolved
2018-04-04 | WAN PMA report | INC000013498652 | incident type wrong for partial outage | Major | Lu Yuan | No | 4/4/2018 Zhu Lin talked to Lu Yuan f2f and reminded him to take care in future | Fully accept |  | Resolved
2018-04-04 | WAN PMA report | INC000013451636 | Ci-Unavailability was not completed | Major | Figueira Jose | No |  | Not accept | No impact on customer/ not real outage | Cancelled
2018-04-04 | WAN PMA report | INC000013404435 | Power issue at customer side, the resolution categorization tier 2 should be Power | Major | Yan Jun | Yes | 4/4/2018 Zhu Lin highlighted in PMA found issue. When update the rfo, resolution categorization was not updated | Fully accept |  | Resolved
2018-04-12 | NOC Daily QC | INC000013599980 | Owner group wrong, CI + wrongly related. Incident type wrong | Major | Liu Jing | No | 4/12/2018 Zhu Lin informed Liu Jing to have a check and Roy will train Liu Jing again | Fully accept |  | Resolved
2018-04-12 | NOC Daily QC | INC000013584111 | Owner group wrong | Major | Figueira Jose | Yes | 4/12/2018 Zhu Lin informed Jose to have a cehck and correct. | Fully accept |  | Resolved
2018-04-12 | NOC Daily QC | INC000013596927 | Incident type, resolution, resolution categorization not correct | Major | Liu Jing | Yes | 4/12/2018 Zhu Lin informed Liu Jing to have a check and Roy will train Liu Jing again | Fully accept |  | Resolved
2018-04-12 | NOC Daily QC | INC000013593828 | incident type is not correct | Major | Francesco Abrahao | Yes | 4/12/2018 Zhu Lin informed Framceso to have a cehck and correct. | Fully accept |  | Resolved
2018-04-12 | NOC Daily QC | INC000013579021 | Inciednt type wrong | Major | Liu Jing | Yes | 4/12/2018 Zhu Lin informed Liu Jing to have a check and Roy will train Liu Jing again | Fully accept |  | Resolved
2018-04-12 | NOC Daily QC | INC000013564667 | connection ID missed in summary | Major | Liu Jing | No | 4/12/2018 Zhu Lin informed Liu Jing to have a check and Roy will train Liu Jing again | Fully accept |  | Resolved
2018-04-12 | NOC Daily QC | INC000013585468 | Summary and resolution is not sufficient | Minor | Francesco Abrahao | No | 4/12/2018 Zhu Lin informed Framceso to have a cehck and correct. | Fully accept |  | Resolved
2018-04-17 | NOC Daily QC | INC000013570172 | Service+ was not updated | Major | XU Gary | No |  | Fully accept |  | Resolved
2018-04-17 | NOC Daily QC | INC000013599980 | Owner group was not changed | Major | Liu Jing | No | 4/17/2018 Zhu Lin informed Liu Jing to check and correct | Fully accept |  | Resolved
2018-04-19 | NOC Daily QC | INC000013641839 | Owner group wrong | Major | Lu Yuan | Yes |  | Fully accept |  | Open
Note on E31: Xie David: Critical: procedure level fault, no ticket, no trouble shooting, no escalation (key word: No) Major: working instruciton level fault, wrong ticket format, wrong ticket routing, wrong action (key word: Wrong) Minor: working log level fault, unclear working log, unclear resolution (Key word: Unclear)
Note on H61: ZHU Lin (CI/OSR3-CN): Cannot correct in SMT, if correct the ticket will be reopened